## To-do list
Project Brady |  | Completed by: | George
|  | Deadline: | [02/04/2015]
Done? | brady | Due By: 02/04/2015 | Notes
No | Prep Work | 2015-01-30 | Approve Project/Yelp API fully functioning/Finalize Project Features
No | Build Base Template Page | 2015-01-31 | I.E. - Basic Bootstrap layout with the search bar up top
No | Stage 1 | 2015-02-01 | Search Page
No | Stage 2 | 2015-02-02 | Search Results Page
No | Stage 3 | 2015-02-03 | Comparison Page - Return 3 blocks of restaurant info
No | Stage 4 | 2015-02-04 | Restaurant Info Page
Done? | Prep | Due By:01/30/2015 | Notes
No | Ensure Yelp Api fully functioning | 2015-01-30 | Work with an Instructor
No | Chat with Instructor | 2015-01-30 | Set up Meeting
No | Finalize Features to build | 2015-01-30
High Priority? | Feature List | Due By | Notes
Yes | Restaurant Search | 2015-02-02
Yes | Restaurant Comparison | 2015-02-02
Yes | Restaurant Info Page | 2015-02-02
No | Restaurant Distance | 2015-02-05
No | Search Restaurant Availability | 2015-02-05